## Sheet1
LLM Knowledge Extractor
Time (min) | Task | Description | Notes
0–5 | Setup Environment | Create virtualenv, install dependencies | python -m venv .venv && source .venv/bin/activate && pip install -r requirements.txt
5–10 | Initialize DB | Run SQLite init script | Ensure knowledge.db is created and table exists
10–20 | Implement Text Utilities | text_utils.py — normalization, tokenization, keywords, sentiment, confidence | Use heuristics for nouns, stopwords
20–30 | Implement LLM Utils | llm_utils.py — call OpenAI API if available, parse JSON, fallback | Include regex fallback for malformed JSON
30–40 | Implement Service Layer | service.py — orchestrate analysis pipeline | Combine LLM + heuristics, boost keywords from title
40–45 | Implement Database Layer | database.py — insert & search functions | Test persistence and JSON parsing
45–50 | Implement API | api.py + FastAPI endpoints /analyze and /search | Use Pydantic models for request & response
50–55 | Testing | Minimal pytest for text_utils, service, database | Include LLM fallback tests
55–60 | Documentation & Docker | Write README.md, ensure Dockerfile works | Include example curl commands and quickstart